## Sheet1
Author | Lessons | Actual_Text | HashTags
Molly Falconer | Lesson1 | Most signups came from organic social. Leverage this in the future by having the guest post earlier/ more frequently. |  | 0.73364 | Tentative | 0.82989 | Analytical
| Lesson2 | Second highest was paid & LI paid direct (the direct signup, not the case study to TripActions with the signup). For the future, run an ad for awareness with the case study, and put more behind direct signup ads. Test more headlines for attracting signups. |  | 0.55174 | Analytical | 0.82989 | Analytical
| Lesson3 | Prepare a newsletter earlier to better leverage email list earlier. Have team members and guest leverage personal contacts earlier. |  | 0.6165 | Sadness | 0.82989 | Analytical
| Lesson4 | Use Leadfeeder company lists for retargeting of companies who visit case studies / resources page (and webinar oage once set up) |  | 0.80547 | Analytical | 0.82989 | Analytical
Ruthie Wyshogrod | Lesson1 | I was not involved in planning the webinar and assumed it was because my help wasn't needed. Based on Molly's lessons I see that there were places where I could have contributed, both in terms of ideas and taking some work off the US marketing team's plate. Next time there is a webinar or larger marketing project I will offer to get involved even if I am not initially brought into the process. |  | 0.93429 | Analytical | 0.87167 | Tentative
Jason Bradley | Lesson1 | Fireside Chat- I am with Daniel on this- it was engaging and extremely informative to see 2 CEO's speak so candidly |  | 0.6165 | Sadness | 0.82989 | Analytical
| Lesson2 | Questions- it was very apparent that some were not from the audience- we should try not to sound as knowledgeable when planting questions |  | 0.89802 | Analytical | 0.82989 | Analytical
| Lesson3 | Virtual Background- I do not think its the computer, because mine is a brand new apple and does the same thing. I think Ariel's backdrop was more intimate and the shamaym one (due to zoom capabilities) just didnt look as good |  | 0.62758 | Joy | 0.89817 | Analytical | 0.71572 | Tentative
Ofir Paldi | Lesson1 | My LinkedIn posts should be less marketing and more as a personal note, That attracted more traction |  | 0.53845 | Analytical | 0.82989 | Analytical
| Lesson2 | I need to be in direct connection with the webinar guest to make sure he is 1. Posting on LinkedIn 2. Get his marketing team engaged to maje their own efforts |  | 0.70754 | Analytical | 0.87481 | Confident
| Lesson 1 | We should have prepared a table with all tasks, core technology and KPI per task. Repeated mistake from Meimad |  | 0.61954 | Analytical | 0.93769 | Confident
| Lesson 2 | Splitting the deck between the 3 of us was good, so is the preparation meeting going over the deck all together |  | 0.67686 | Joy | 0.5986 | Confident
| Lesson 3 | Contractors - if we present them as a project based and not hourly based, we need a high level SOW for their part |  | 0.80246 | Analytical | 0.82989 | Analytical
Dror | Lesson 1 | In such meeting, there should be a leading use case, that you can refer to it all the time when you speak about the module (Meet John, he is a [$Role] in a [$team_name], and this is how his day-2-day looks with [new] Shamaym). It will ease the cognitive load on the examiner along the hours, and make it easier to understand where the module fit in the puzzle. |  | 0.8829 | Analytical | 0.82989 | Analytical
| Lesson 2 | Having illustrations (mock-ups, screenshots) helps deliver the technical message more easily. As much as possible. |  | 0.72078 | Analytical | 0.94485 | Tentative
| Lesson 3 | The examiner is looking on the company as a whole, not only on the specific technology requests. We should come prepare with examples of all the achievements up-to-date, in slides he can take forward (marketing, CS, customers, sales). Graphs of YoY are preferred. |  | 0.9415 | Analytical | 0.84202 | Confident
Molly Falconer | Lesson 1 | Went well but a few things to make it better: -better coordinate w guests' marketing team, maybe a prep call w everyone ahead of time - need to assign guests as panelists so they get a specific link to join, do this immediately & send to their team - send out calendar invite immediately upon registration (can we do this through mailchimp) -I left less time for questions bc there were none, then people added them all at once. More time for questions. -Better mikes for participants. Sound was ok but could have been clearer w headsets. |  | 0.6165 | Sadness | 0.82989 | Analytical
Ofir Paldi | Lesson 1 | Questions from audience is better that the 1:1. Since I knew there is 1 question I kept asking and took 30 min. A mistake. People are asking most questions when this part starts. leave 25 min for questions (Can always dd another question at the end) |  | 0.67376 | Sadness | 0.60807 | Confident | 0.97625 | Analytical
| Lesson 2 | Next Webinar have to be with different computer if I'm planning to use virtual background |  | 0.64599 | Confident | 0.64639 | Analytical
| Lesson 3 | As the host - I need to have at least 8 questions ready. |  | 0.84211 | Analytical | Analytical
| Lesson 4 | Make sue they question I prepared are not too similar to each other. Answers usually have more information and than it cancel other planned questions |  | 0.63179 | Tentative | 0.99116 | Analytical
| Lesson 5 | We need to build a structured process/checklist for best practices to market those webinars and to get high conversion rate between enrollments to actualparticipants |  | 0.6165 | 0.82989 | Analytical
Boaz Hermon | Lesson 1 | Adding some slides (very few) or a short movie can help with having some kind of break between sessions |  | 0.93782 | Tentative | Analytical
Daniel Friedman | Lesson 1 | Having a "fireside chat" webinar was actually quite engaging. |  | 0.66021 | Confident | Analytical
| Lesson 2 | Need to balance the "intent" of the webinar - is it meant to be for sales purposes, educational, etc.? |  | 0.72424 | Analytical | Analytical
Pat Hart | Lesson 1 | I need to practice and refine my product DEMO presentation. I have scheduled Slack integration training with Ophir next week. |  | 0.59612 | Analytical | Analytical
| Lesson 2 | Good modified pre-takeoff meeting with team manager from TripAction. I need to better define "flights" and the what they need to debrief. I will schedule quick meeting or communicate over email to ensure we are clear before takeoff ("relaunch") with her team. |  | 0.74766 | Analytical | Analytical
| Lesson 1 | CS team is taking a more data driven approach to analyzing product usage for customers. It will take some time, but initial indications from data is that employees are much more likely (64%) to add lessons to a collaborative debrief if the manager initiates it, compared to around 15% when initiated by Shamaym Assistant. Lesson is that Shamaym is tool for leaders to use within their organization to improve culture and performance and should not be driven by CSM. |  | 0.84639 | Tentative | 0.91344 | Analytical
| Lesson 2 | We discussed bringing back bi-weekly meetings, led by Account Managers, to review existing accounts with the CSMs. Recommend US team attend a few of these meetings to better understand status of existing accounts. |  | 0.71153 | Analytical | Analytical
Daniel Friedman | Comment | Thanks Pat, per your Lesson #2.....I'd love to join. |  | 0.8647 | Joy | 0.68777 | Analytical
Danny Baralya | Lesson 1 | We need to guide and give more tools for our team: - How to choose who should I address and compose a list - Kick-off meeting - Presenting the goals and method - Bi-weekly status update meeting - Method should be flexible to each managers style | #Sales | 0.6165 | 0.82989 | Analytical
Amit Kochavi | Lesson 1 | I should be honest - I hate asking favors from people. Calling clients and asking them to hook me up with other leads is against my personality, and that is why i reacted so slowly. I truly hate being in this position. What should i do better next time? - Reflect my thoughts, and "put things on the table". - ask for help such as pre-written mail (i did it but too late), and maybe a meeting with Sivan or Danny - dedicated to calling people or sending mails. This is the help i needed to overcome my personal challenge. |  | 0.5159 | Fear | 0.58503 | Anger | 0.65593 | Tentative | 0.79888 | Analytical
Ofir Paldi | Lesson 1 | We need a brief meeting when starting this kind of project next times - objectives, methods, best practice | #Sales | 0.72982 | Joy | 0.58393 | Tentative
| Lesson 2 | During the meeting, each participant need to identify the top connections he is going after |  | 0.53262 | Analytical | Analytical
Sivan Berger-Mor | Lesson 1 | Referrals are not something you do "by the way", you need to have a plan, you need to have simulations, you have to give the sales rep all they need to fill confidant. |  | 0.6165 | 0.82989 | Analytical
| Lesson 2 | In Shamaym, nothing works better than competition between the account managers... this is what Ill do next time |  | 0.78401 | Sadness | Analytical
Moshik Schur | Lesson 1 | Oren didn't like this request. He was polite and pushed back gently. I'm not sure this is the best practice for US clients (or Israelis with us mentality) We should assume that happy client will find the way to talk about us. |  | 0.71049 | Joy | 0.93907 | Tentative | 0.69838 | Analytical
| Lesson 2 | Joint LinkedIn posts with existing clients are much more effective. As CSMs we need at least 1 joint posts with each client |  | 0.92443 | Analytical | Analytical
Boaz Hermon | Lesson 1 | We need to be prepared with a "demo". One option is the 3-4 "tabs" that shows the sequence/flow of the debrief. The other option is to send a collaborative debrief to the manager "live" during a 1:1 | #Product #Customer_success | 0.72464 | Tentative
| Lesson 2 | What is the optimum "window" from the request to the publish? We are having few use-cases: (1) Open Monday morning and publish just before the weekly (2) 24 hours of window (3) a whole week for a window. What works best? we should know in a few weeks. |  | 0.64778 | Tentative
| Lesson 3 | When we introduce the auto-collab to a manager - we need to come up with a one-slide (flow) and one more to enter details (when to request to collab? when to publish? and sometime - what is the topic). I will prepare 2 slides about that. |  | 0.81456 | Tentative
| Lesson 4 | How does the format should look like? As for now we have the "what is the topic" and "lessons". Should we add "time to publish"? should we add an example of a good lesson (this example will be as the 1st lesson of Shamaym assistant). As for now - we are checking both options. what do you think is better? |  | 0.92659 | Analytical
Amit Kochavi | Comment | Thanks Boaz for this 1. Demo- this Thursday. this will include a demo for the manager, and don't for team members. 2. Other topics raised - This is still premature to set rules and best practices. The important thing is to document each trial, and add comments. *everyone has to make sure we are not missing even collab sent without documenting it. * another small question - why did you debrief this in a "Random debrief" format? this is pure CS debrief. Amit |  | 0.59142 | Joy
Yuval Zach | Comment | Thanks Boaz for this 1. Demo- this Thursday. this will include a demo for the manager, and don't for team members. 2. Other topics raised - This is still premature to set rules and best practices. The important thing is to document each trial, and add comments. *everyone has to make sure we are not missing even collab sent without documenting it. * another small question - why did you debrief this in a "Random debrief" format? this is pure CS debrief. Amit |  | 0.59142 | Joy
Boaz Hermon | Comment | Thanks Amit and Yuval! First - I chose to write this debrief under "random debrief" because (1) it is not a CS daily and (2) It is not a meeting with a client. So, my thoughts on that (1) I would suggest, as I do with other clients, to have only one team for CS with a "what is the topic" of (1) CS daily/weekly (2) Meeting with a customer (3) other. Also, I wanted to share this debrief with the product team - for that I should have written the debrief in a CS team and share it with Maayan/Dror/Ophir. As for the auto-collaboration: 1. I, personally, don't like reminders. So - as much as I like the idea of a reminder 24 hours before publication I think it is better to collaborate 24 hours before publishing. 2. Example - totally agree yuval, they should know how to debrief. But imagine a team that last time I met them was about 3 month ago, they wrote some debrief but most of them are not so good. Now - what would you do? 3. I understand this is premature, but we already have some experience - thought this is a good opportunity to have a "pulse-check". Boaz |  | 0.53839 | Joy | 0.51064 | Analytical | 0.70865 | Tentative
Molly Falconer | Lesson 1 | Creating more content to drive traffic to the website. Need to create different screengrabs of different features from the platform, and create more content around our "why", highlighting the methodology and the overall importance of debriefing to the goal of culture change, rather than just features. Next week will be scripting 2 pcs of content; one for "why Shamaym" and one for upcoming remote work campaign. |  | 0.73566 | Analytical | 0.84639 | Tentative
Daniel Friedman | Comment | Excellent debrief, especially as we look into additional marketing activities next week. Have a great weekend |  | 0.90702 | Joy | 0.85701 | Analytical
Jason Bradley | Lesson 1 | His lack of filler language can strengthen my demo- i am going to stop using ah and um | #Proactivity#Communication#Prerequisites#Checklist | 0.72424 | Analytical
| Lesson 2 | Did not feel read- work on delivery |  | 0.6817 | Tentative
Daniel Friedman | Comment | Thanks for the debrief Jason, it's definitely a process on my end. We just need to keep on testing, reflecting, reviewing, and testing again..... |  | 0.82543 | Analytical
|  | I like you, but as a friend |  | 0.55206 | Joy | 0.6817 | Tentative
|  | Extremely nice service. Convenient and satisfactory product. Would definitely recommend the product |  | 0.50806 | Joy | 0.95293 | Analytical | 0.98672 | Confident
|  | Appreciated the good customer service. |  | 0.75308 | Joy | 0.88228 | Analytical
|  | Today the weather is so nice. I could go to the beach in this lovely weather. Or we could do a barbeque in the backyard. |  | 0.7475 | Joy | 0.98652 | Tentative
|  | Plastic manufacturing companies should be stop manufacturing right away. They have been causing so much damage to the environment. Sulfer dioxide and sulfer monoxide causes the ozone layer to leak. |  | 0.57227 | Sadness
|  | Dear Pigalle fans, it is hard to believe that in this day and age there are still uneducated, unitelligent, unpolished human beings out there that still go out to eat, but there are, and this women proves my point. If anyone has ever has a problem at any restaurant, food or service, you complain or bring it to their attention, at the restaurant, not on someone's facebook page. This is an ignorant and disrespectful way of carrying ones self when in a public restaurant. |  | 0.71096 | Analytical | 0.93198 | Tentative
This place is horrible
|  | An disabled person reserved their seat almost a year ago, then Delta came back a week before the trip, said thery double booked his seat and moved him to a seat that wasn't usable for him. Customer service refused to help him. He asked customer service and disability relations to move the other passenger to another seat, they simple said 'No'. Finally the relationship rep moved him to Coach... really... This is how Delta treats people with disabilities ?????? |  | 0.50037 | Joy | 0.84622 | Analytical